## Sheet1
AWS setup (for Jenkins) |  |  | When Start | When End | Status | Outcome | Issues |  |  |  | Duration
| Setup UAM for Jenkins account |  | Session 4 |  |  |  |  | Session 1 | 2020-06-27 | 10:30 - 12:30 | 2 | Cloudformation, setup kubernetes cluster
Jenkins setup | [7 empty] | Sesion 2 | 2020-06-27 | 15:00 - 17:00 | 2
| Installation of Jenkins on Microservers server |  | Session 4 |  |  |  |  | Session 3 | 2020-06-27 | 19:00 - 21:00 | 2
| Login to Jenkins |  | Session 4 |  |  |  |  | Session 4 | 2020-06-28 | 05:00 - 09:00 | 4 | Jenkins, setup asw
| Installatin of BlueOcean |  | Session 4 |  |  |  |  | Session 5 | 2020-06-28 | 11:00 - 13:00 | 2 | Office work
| Installation of Plug-ins |  | Session 4 |  |  |  |  | Session 6 | 2020-06-28 | 15:00 - 17:00 | 2
| Run a simple pipeline, Decide pipeline strategy (rolling or blue/green) |  | Session 4 |  |  |  |  | Session 7 | 2020-06-28 | 19:00 - 23:00 | 6
| Setup for Linting |  | Session 4 |  |  |  |  | Session 8 | 2020-06-28 | 05:00 - 09:00 | 4
| Setup for Security |  | Session 4 |  |  |  |  | Session 9 | 2020-06-28 | 19:00 - 21:00 | 2
CloudFormation | [7 empty] | Session 10 | 2020-06-28 | 22:00 - 24:00 | 2
| Plan stack for server (remote) - EC2 instances |  | Session 1 | Done |  |  |  | Session 11 | 2020-06-29 | 05:00 - 09:00 | 3
| Choose AMI |  | Session 2 | Done
| Develop scripts to build serevr |  | Session 2 | Done
| Test the scripts and troubleshoot any errors |  | Session 3 | Done
Kubernetes Cluster | Try setting up kubernetes cluster using scripts in cloudformation |  | Session 3 | Done
| Initialise Kubenetes cluster |  | Session 3 | Done
Python Code
| Environment setup |  | Session 5
| Python code |  | Session 5
| Pylint |  | Session 5
Docker
| Setup Docker environment and scripts (re-use Microservices project) |  | Session 1
| DockerFile Hadolint |  | Session 5
| Docker Build |  | Session 5
| Setup Docker Hub |  | Session 6
| Push Docker Image to Docker Hub |  | Session 6
| Test docker buikd |  | Session 6
GitHub | Setup GitHub Repository for Project |  | Session 1
Integration
| Write Jenkinsfile pipeline |  | Session 7
| Create a Blue Branch and a Green Branch |  | Session 7
| For each Branch, |  | Session 7
| Stage 2 - Test Docker container deployment on remote server |  |  | Is pipeline under a branch?
Stage 3 - Locus Load Testing
Pipleline server Build (Branch Blue or green) | Stage 1 - Deploy the server using CloudFormation | one-time | Session 8
Pipeline Build Docker | Stage 2 - a. Container deployment on remote server b. Linting code, c. scanning images, d. load testing | continuous | Session 8

## Sheet2
Project Name | FinalProjectDevOps
Application Name | finalpjdevops
Pipeline Name
Jenkins user name | Jenkins
Github repository name